## Sheet1
Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Planning
Gather requirement of Swiss Garden Hotel | bar: Week 1
Verify digital platform function | bar: Week 2
Analysis
Investigate business processes | bar: Week 3
Survey | bar: Week 4 to Week 5
Design
Design digital platform user interface | bar: Week 6 to Week 7
Create physical model | bar: Week 8 to Week 9
Implementation
Start digital platform development | bar: Week 10 to Week 11
Add on additional features | bar: Week 12 to Week 13
Debugging and finalize | bar: Week 14 to Week 15
System Security and Support
System maintainence | bar: Week 16